## Slide 1
AGILE & SCRUM
Mastery Program
A Complete Professional Training on SDLC, Agile, Scrum,
User Stories, Story Points, Burndown Charts & JIRA
Senior Project Manager & Architect | 30+ Years Industry Experience
Corporate Training Series

## Slide 2
Course Roadmap — Your Learning Journey
OVERVIEW
01
Introduction to SDLC
02
The Agile Manifesto
03
Scrum Framework
04
User Stories & Epics
05
Story Pointing & Burndown
06
JIRA — Scrum Boards in Practice
Each module builds on the previous — master the WHY before the HOW.

## Slide 3
MODULE 1
Introduction to SDLC
Understanding the foundation of all software development processes

## Slide 4
What is SDLC?
MODULE 1
Software Development Life Cycle
A structured, phase-by-phase process for planning, building, testing, and delivering software professionally — bringing order to what was once chaos.
🏥 Think of a Hospital
Patients follow: Reception → Triage → Diagnosis → Treatment → Recovery → Discharge. Each step has a clear purpose. You cannot discharge before recovery. Software follows the same logic.
WHY IT EXISTS
The 1960s Software Crisis:
Projects were late, over budget,
or completely failed.
Without structure, developers
build the wrong thing.
SDLC brought predictability,
quality & accountability.
It is the 'recipe' for building
complex software systems.
"Every successful software project follows SDLC — consciously or instinctively."

## Slide 5
The 7 Phases of SDLC
MODULE 1
1
Planning
WHY?
Feasibility, budget, resources, risk
2
Requirements
WHAT?
Functional & non-functional requirements
3
Design
HOW?
Architecture, database, UI/UX design
4
Development
BUILD
Actual coding by developers
5
Testing
VERIFY
Unit, integration, UAT, security tests
6
Deployment
SHIP
Release to production, go-live
7
Maintenance
GROW
Bug fixes, enhancements, monitoring
🏦 PAYEASY BANKING PROJECT: The bank applies all 7 phases — from planning a $500K investment through maintenance of a live system serving 500,000 customers.

## Slide 6
Waterfall Model — The Traditional Approach
MODULE 1
WATERFALL MODEL
1. Planning
2. Requirements
3. Design
4. Development
5. Testing
6. Deployment
⚠️ Fatal Flaw: Requirements locked at start.
Customer sees product only at the end — 12 months later!
5 ROOT PROBLEMS AGILE SOLVED
1
Requirements change — business evolves
2
Late feedback — customer sees product at the end
3
High risk — huge investment, no working software
4
No flexibility — changing direction is expensive
5
Docs over collaboration — misinterpretation rife
Standish CHAOS Report: Only 29% of Waterfall projects succeeded on time and on budget. 52% were late or missing features. 19% failed completely.

## Slide 7
MODULE 2
The Agile Manifesto
The 68-word document that changed software development forever — February 2001, Utah, USA

## Slide 8
Birth of Agile — February 2001
MODULE 2
17 experienced software veterans gathered at Snowbird Ski Resort, Utah. Frustrated by heavyweight, documentation-heavy processes that were failing projects worldwide, they wrote a manifesto that would transform the industry.
THE AGILE MANIFESTO — 4 CORE VALUES
Individuals & Interactions
OVER
Processes & Tools
Working Software
OVER
Comprehensive Documentation
Customer Collaboration
OVER
Contract Negotiation
Responding to Change
OVER
Following a Plan
"While there is value in items on the right, we value items on the LEFT more."

## Slide 9
The 12 Agile Principles
MODULE 2
1
Customer satisfaction through early & continuous delivery
2
Welcome changing requirements, even late in development
3
Deliver working software frequently — weeks, not months
4
Business & developers must work together daily
5
Build around motivated individuals — trust them
6
Face-to-face conversation is the most efficient communication
7
Working software is the primary measure of progress
8
Agile promotes sustainable development — constant pace
9
Continuous attention to technical excellence
10
Simplicity — maximize the work NOT done
11
Best architectures emerge from self-organizing teams
12
Regularly reflect and adjust to become more effective

## Slide 10
MODULE 3
Scrum Framework
Roles, Events, Artifacts — the world's most popular Agile implementation

## Slide 11
The Scrum Framework — Big Picture
MODULE 3
Scrum structures work into short, fixed cycles called Sprints. At the end of every Sprint, the team delivers real, working software.
PRODUCT
BACKLOG
▸ Feature 1
▸ Feature 2
▸ Feature 3
▸ Feature 4
▸ Feature 5
▸ ...50+ items
Sprint
Planning
SPRINT (2 Weeks)
Sprint Backlog
✅ Story A
🔄 Story B
⏳ Story C
⏳ Story D
☀️ Daily Standup — 15 min every morning
SPRINT
REVIEW
Demo working
software to
stakeholders
SPRINT
RETRO
What went well?
What to improve?
OUTPUT: INCREMENT — Working, potentially shippable software delivered at the end of every Sprint

## Slide 12
The 3 Scrum Roles
MODULE 3
No hierarchy — all three roles are peers with distinct, non-overlapping responsibilities.
PRODUCT OWNER
"The WHAT"
Maximizes product value
Owns & orders the Product Backlog
Single voice of the customer
Accepts or rejects completed work
Must be available daily
Makes final priority decisions
📌 Priya Sharma — Senior Digital Banking Manager
Decides feature order and accepts completed sprints
SCRUM MASTER
"The HOW"
Servant leader — serves the team
Removes impediments & blockers
Protects team from distractions
Coaches Scrum values & practices
Facilitates all Scrum events
NOT a project manager
📌 Rajiv Menon — Certified Scrum Master
Coaches team, removes blockers, protects sprint
DEVELOPERS
"The BUILD"
Cross-functional — all skills in-house
Self-organizing — nobody assigns tasks
5–9 people (two-pizza rule)
Collectively accountable
Estimate their own work
Design, build, test & deploy
📌 7-person team: Backend, Frontend, UX, QA, DB, DevOps
Self-assign tasks during Sprint Planning

## Slide 13
The 5 Scrum Events
MODULE 3
All 5 events occur within the Sprint. The Sprint is the container — all other events happen inside it.
1
The Sprint
2 Weeks
👥 Whole Team
Fixed-length iteration — the engine of Scrum. Has a clear Sprint Goal. No changes that endanger goal.
2
Sprint Planning
Max 4 hrs
👥 Whole Team
WHY is Sprint valuable? WHAT can be done? HOW will it be built? Output: Sprint Backlog.
3
Daily Scrum (Standup)
15 min/day
👥 Developers
3 questions: What did I do yesterday? What will I do today? What's blocking me? NOT a status report.
4
Sprint Review
Max 4 hrs
👥 + Stakeholders
DEMO working software. Get real feedback. Update Product Backlog. PO accepts/rejects completed work.
5
Sprint Retrospective
Max 3 hrs
👥 Scrum Team
What went WELL? What went WRONG? What should we TRY? 3 specific action items for next Sprint.

## Slide 14
MODULE 4
User Stories & Epics
The language of Agile — turning business needs into deliverable software

## Slide 15
The User Story Formula
MODULE 4
As a
[ TYPE OF USER ]
I want
[ GOAL OR FEATURE ]
So that
[ VALUE / BENEFIT ]
The 3 C's of User Stories
CARD
A brief, physical or digital card. Small size forces brevity — it is a PLACEHOLDER for conversation, not a full specification.
CONVERSATION
The real value. Direct discussion between PO, developers, and QA surfaces requirements no analyst could anticipate alone.
CONFIRMATION
Acceptance Criteria — specific, testable conditions that define when the story is truly DONE. Written BEFORE development begins.
🏦 PayEasy Example: "As a PayEasy retail customer, I want to transfer money to a family member's account instantly, so that I can support them financially without visiting a bank branch."

## Slide 16
The Agile Planning Hierarchy — Epics to Tasks
MODULE 4
THEME / PRODUCT VISION
▸ PayEasy: A complete digital banking platform replacing branch banking
▼
EPIC
▸ Fund Transfers: All features enabling customers to move money
▼
USER STORY
▸ As a customer, I want to transfer to a new recipient (13 pts)
▼
TASK / SUB-TASK
▸ Build POST /api/transfer endpoint | Write unit tests | Design UI form
Size Rule: If it can be done in ONE Sprint → Story. If it takes MORE than one Sprint → Epic (break it down).

## Slide 17
INVEST — Six Qualities of an Excellent User Story
MODULE 4
I
INDEPENDENT
Can be developed without depending on another story. Use vertical slicing — each story goes end-to-end (UI + API + DB).
N
NEGOTIABLE
Details are flexible — not a rigid contract. The WHAT and WHY are fixed. The HOW is always open to discussion.
V
VALUABLE
Every story must deliver real value to a user or the business. If you can't articulate the value — don't build it.
E
ESTIMABLE
Team must be able to estimate effort. If they can't — the story is too vague, too large, or involves unknown technology.
S
SMALL
Must be completable within ONE Sprint. Anything larger must be split. Large stories are disguised Epics.
T
TESTABLE
Must have clear Acceptance Criteria that can be verified with specific pass/fail test scenarios. Vague stories can't be tested.

## Slide 18
Acceptance Criteria — The Definition of Done for a Story
MODULE 4
AC are the specific, testable conditions that must be true for a story to be complete.
Written BEFORE development. Agreed by PO, Developer, and QA (the Three Amigos).
GIVEN / WHEN / THEN FORMAT
GIVEN
the starting context/condition
WHEN
an action is taken by the user
THEN
the expected outcome occurs
PayEasy Fund Transfer — Sample Scenario:
GIVEN I am logged in AND have ₹10,000 balance
WHEN I transfer ₹2,000 to a valid account + OTP verified
THEN my balance shows ₹8,000 immediately
AND SMS confirmation sent to both parties
AND transaction appears in history instantly
Common Story Mistakes to Avoid
✗ Writing from the SYSTEM's perspective (not user)
✗ Skipping the 'So that' — no clarity on value
✗ Writing Tasks as Stories (no user value)
✗ Writing Epics as Stories (too large for 1 Sprint)
✗ Vague AC: 'should work correctly' is untestable
✗ Horizontal slicing instead of vertical slicing
✗ Technical jargon in user-facing stories
✗ AC written after development begins

## Slide 19
MODULE 5
Story Pointing & Burndown Charts
How Agile teams estimate work, predict the future, and track sprint health

## Slide 20
Story Points — Relative Estimation, Not Hours
MODULE 5
Story Points measure relative complexity, effort, and uncertainty — NOT time. Teams are good at comparing work, not predicting exact hours.
THE FIBONACCI SCALE — 1 · 2 · 3 · 5 · 8 · 13 · 21 · 34 · 55 · 89
Why Fibonacci Numbers?
Gaps GROW as stories get bigger → forces honesty about uncertainty
Small stories (1-3): precision is possible
Medium stories (5-8): direction is clear
Large stories (13-21): gaps signal 'split this!'
Prevents analysis paralysis — is this a 6 or 7? With Fibonacci: is this 5 or 8?
Larger gaps mean: you don't know enough yet — have a conversation first
Planning Poker
1
Trivial — almost nothing
3
Small — straightforward
8
Large — some unknowns
13
Very large — complex
?
Need more info first
∞
Must split this story

## Slide 21
Team Velocity — The Predictability Engine
MODULE 5
Velocity = Story Points completed per Sprint (average over time). Used for FORECASTING — never for measuring performance or comparing teams.
PayEasy Team Velocity History
18
S1
22
S2
26
S3
24
S4
27
S5
25
S6
Avg: 24 pts
Release Forecast
Remaining work:
190 pts
Avg velocity:
24 pts/Sprint
Sprints needed:
~8 Sprints
Sprint length:
2 weeks
Forecast:
≈ 4 months
⚠️ WARNING
NEVER set velocity targets or compare across teams. Use it only for planning.

## Slide 22
Burndown Chart — The X-Ray of Your Sprint's Health
MODULE 5
A Burndown Chart tracks remaining Story Points vs. time. Updated daily. The SHAPE of the line tells the Sprint's story.
PayEasy Sprint 3 — Burndown Chart
Story
Points
Remaining
26
20
14
8
0
⚑ Blocked
Big drop!
Team rallied
✅ Day 9 — Complete
(1 day early!)
D0
D1
D2
D3
D4
D5
D6
D7
D8
D9
Legend: --- Ideal ── Actual
5 Chart Patterns
✅ Ideal Sprint
Smooth diagonal — team is on track
⚠️ Slow Start
Flat early — blocked or unclear stories
❌ Scope Creep
Line RISES — work added mid-Sprint
⚠️ Sandbagging Cliff
Flat → cliff at end — horizontal slicing
✅ Scope Reduction
PO removed stories to protect quality

## Slide 23
MODULE 6
JIRA — Agile in Practice
The command center of every modern Agile team — Scrum boards, sprints & reports

## Slide 24
What is JIRA?
MODULE 6
JIRA by Atlassian is the world's #1 Agile project management tool — used by 65,000+ companies. It digitizes everything: backlogs, sprints, boards, burndown charts, and velocity reports.
SCRUM TERM
JIRA EQUIVALENT
Product Backlog
Backlog view
Sprint Backlog
Active Sprint on Board
User Story
Story (Issue Type 🟦)
Epic
Epic (Issue Type 🟪)
Bug / Defect
Bug (Issue Type 🟥)
Story Points
Story Points field on each ticket
Burndown Chart
Reports → Burndown Chart
Velocity
Reports → Velocity Chart
Blocker / Impediment
Flagged ticket ⚑ (red flag icon)
JIRA doesn't introduce any new concepts — it implements everything you already know from Scrum.

## Slide 25
The JIRA Scrum Board
MODULE 6
The Board is the daily operational view of the active Sprint. Cards flow left to right as work progresses through your workflow.
TO DO
Transfer Confirm.
5 pts · [Arun]
Recipient Lookup
3 pts · [Lakshmi]
IN PROGRESS
Transfer API
8 pts · [Arun]
Transfer UI
5 pts · [Suresh]
DB Schema
[Lakshmi]
IN REVIEW
OTP Integration
5 pts · [Meera]
⚑ Perf Test
BLOCKED · [Farhan]
DONE
✅ Error Handling
3 pts
✅ Login Feature
5 pts
Sprint 3 Goal: 'Customers can securely transfer funds with real-time confirmation' | 26 Story Points | Feb 1 – Feb 14

## Slide 26
Sprint Lifecycle in JIRA
MODULE 6
1
Create Sprint
Set Sprint name, start/end dates, Sprint Goal in JIRA Backlog view
→
2
Sprint Planning
Drag Stories from Backlog into Sprint. Run Planning Poker. Add Story Points. Set Sprint Goal.
→
3
Start Sprint
Click 'Start Sprint'. Board activates. Burndown begins. Team receives notification.
→
4
Daily Management
Team drags cards across columns. Flag blockers immediately. SM removes impediments same day.
→
5
Complete Sprint
Click 'Complete Sprint'. JIRA asks where unfinished stories go (Backlog or next Sprint). Sprint Report auto-generated.
JIRA BEST PRACTICES
Update cards DAILY
Write AC in the Story
Comment all decisions
Link related issues
Never delete — close with reason
Refine backlog mid-sprint

## Slide 27
JIRA Reports — Intelligence for Every Decision
MODULE 6
JIRA auto-generates all Agile reports from your team's daily card movements. No manual data entry required.
Burndown Chart
❓ Are we on track this Sprint?
Updated daily from card movements. Reveals blockers, scope creep, and sandbagging patterns. The daily health check.
Velocity Chart
❓ How much can we plan next Sprint?
Shows committed vs completed points per Sprint. Used for release forecasting. NEVER used to pressure teams.
Sprint Report
❓ What did we achieve this Sprint?
Auto-generated on Sprint completion. Shows completed, incomplete, and added issues. Evidence for Sprint Review.
Epic Burndown
❓ When will this Epic be complete?
Tracks story completion within a specific Epic. Shows feature-area progress at a strategic level.
Cumulative Flow
❓ Is work flowing through our process?
Shows issue volume in each workflow column over time. Thick bands reveal bottlenecks — e.g., review stage overloaded.
Release Burndown
❓ Will we launch on time?
Strategic view across all Sprints. Shows if team will finish by target release date. Enables scope or timeline adjustments.

## Slide 28
AGILE & SCRUM
Mastery Summary
01
SDLC
7-phase structured process · Waterfall's fatal flaw · 5 root problems
02
Agile
4 Values · 12 Principles · Mindset over ceremonies
03
Scrum
3 Roles · 5 Events · 3 Artifacts · 5 Values
04
User Stories
As a / I want / So that · INVEST · Acceptance Criteria · Epic hierarchy
05
Estimation
Story Points · Fibonacci · Planning Poker · Velocity · Burndown Charts
06
JIRA
Scrum Board · Sprint lifecycle · Reports · Best practices
"Agile isn't installed — it's a culture of trust, transparency, continuous improvement, and relentless focus on customer value."